FIRST 90 DAYS — NORTHEAST REGION

Evan Parnell  ·  Regional Laboratory Operations Director, Northeast

A working outline offered for discussion, not a finished plan — it should change once I can see the region’s actual numbers.

Operating Principle

A region of independently accredited laboratories with different scopes, licences and histories cannot be managed as one until its numbers mean the same thing at every site. Measurement first, standardization second, structure last. I would rather be deliberately slow for thirty days than reorganize something in week two that I do not yet understand.

Days 1–30 · Listen and measure. Change almost nothing.

- Visit every laboratory and service center in the region — time at the bench, not only in the office.

- Sit with each site’s leadership, and separately with analysts and sample receiving. The people who receive samples and release data know where the losses are.

- Pull twelve months by site: revenue and margin to plan, cost per sample, on-time turnaround, reanalysis and rework, overtime, instrument uptime, open corrective actions, accredited scope.

- Determine whether every site defines those the same way. On-time turnaround especially — received-to-reported or scheduled-to-reported is where variance hides.

- Map the region honestly: which sites are full-service laboratories, which are focused benches, which are service centers, and where each site’s accredited scope begins and ends.

- Understand the top clients per site, and what each would say about us if I called them.

Deliverable at 30 days: a written baseline of the region as it actually is, including where our numbers are not yet comparable.

Days 31–60 · Install one operating cadence.

- One weekly metric set, defined identically everywhere, small enough that site leaders can produce it without a project: backlog and aging, on-time turnaround, open corrective actions, overtime.

- One monthly operating review per site, same agenda: performance to plan, capacity, quality, people.

- Fix definitions before setting targets. A target on an inconsistent measure produces reporting behavior, not operating improvement.

- Publish the region’s numbers internally so sites can see each other. Visible comparability drives more improvement than any target set from Baltimore.

- Protect what works. Where a sub-region already performs, the cadence should confirm it and get out of the way. Technical authority stays with the technical leaders who hold the licences.

Deliverable at 60 days: a single regional operating review running on common definitions.

Days 61–90 · One visible win, and a plan.

- Fix the most expensive addressable problem found in the first thirty days, end to end, at one site, with a number attached. Usually a turnaround bottleneck — often data review queued behind one or two approvers — or a reanalysis rate nobody has priced.

- Bring an answer to the 2027 demand question. Two federal drinking-water deadlines land that year, and compliance samples arrive in the final quarters before a deadline rather than evenly. Capacity, staffing and scheduling should be decided in advance, not absorbed.

- Deliver a written twelve-month regional plan: capacity and capital, accredited scope, staffing and development, and where growth comes from.

Deliverable at 90 days: one proven improvement, and a plan the region has agreed to.

What I Would Want From You

- Clarity on which sites are mine, and whether the P&L is cut by site, by division, or by region.

- Clarity on what I can decide and what comes to you first.

- An introduction to my finance counterpart, and access to whatever facility-level tracking already exists.

- Patience for thirty days of questions before I propose changes.

What I Will Not Do

Reorganize a functioning team before I understand why it works. Set targets on measures that are not yet consistent. Trade defensible data for a faster month — a late result is recoverable, a result that does not hold up is not.